## Sheet1
THIS IS A GANTT CHART FOR ONLINE BOOKSTORE WEBSITE
Starting from 18th of Oct 2021
|  |  |  | Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 | [5 empty] | Week 4 | [5 empty] | Week 5 | [5 empty] | Week 6 | [5 empty] | Week 7 | [5 empty] | Week 8 | [5 empty] | Week 9 | [5 empty] | Week 10
Task No | Phase | Sub-task | Resource | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat
1 | Initiation
2 |  | Identify requirements & objects | All
3 |  | Create backup plan | PM
4 |  | Market research | PM
5 |  | Produce servers | PM
6 |  | Select security provider | PM
7 |  | Implement backup plan
8 | Implementation
8 |  | Admin module | Arch & Dev
9 |  | User module | Arch & Dev
10 |  | Testing prototype | QA
11 |  | Live testing | QA
12 |  | Document approved build | PM
13 | System Performance
14 |  | Install servers | Dev
15 |  | Test connectivity | QA
16 |  | Configure load balancing | QA
17 |  | Performance testing | QA
18 |  | Finish project | All