## Three-Point Project Cost Est.
Project Title; Project Manager | online bookstore system | Total budget: 1200$ |  | RUNNING WEIGHTED AVERAGE TOTAL: |  | 11813.3333
DETAILS |  |  | THREE-POINT COST ESTIMATE SCENARIOS |  |  | WEIGHTED AVERAGE
Duration | TASK DESCRIPTION | GATHERED BY | BEST-CASE | MOST LIKELY / REALISTIC | WORST-CASE
2 months | Identify requirement and object, create backup plan, market research, produce servers, select security provider, implement backup plan | Project management: Phạm Quang Văn | 2900 | 3000 | 3100 | 3000
2 months | responsible for helping their team members with the technical aspects of their jobs, such as coding and programming. They may also explain new projects to their team and troubleshoot any problems that occur. | Tech leader: Phí Đình Đạt | 500 | 620 | 700 | 613.3333
2 months | product implementation and development | Developer: 8 | 1600 | 2000 | 2500 | 2016.6667
2 months | Preparing drawings, blueprints, specifications, and construction documents, conducting research and compiling reports on feasibility and environmental impact, managing project teams and collaborating with other construction professionals | Architects: 3 | 1250 | 1500 | 1800 | 1508.3333
2 months | Reporting and Tracking Defects, participating in Evaluating exit criteria, and Closing Test Cycle | tester and tester leader | 450 | 300 | 500 | 358.3333
2 months | Marketing logistics involve planning, delivering and controlling the flow of physical goods, marketing materials and information from the producer to the market. | Marketers & Logisticians | 1000 | 1600 | 1800 | 1533.3333
2 months | Other costs (water,supply,unexpected risk,...) |  | 2500 | 2800 | 3000 | 2783.3333
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.