## WBS
Work Breakdown Structure | [5 empty] | ONLINE BOOKSTORE SYSTEM
Project Start |  | 2021-10-18
Level | WBS | Task Description | Assigned To | Start | End | Notes
1 | 1 | Phase 1: Initiation |  | 2021-10-18 | 2021-11-01
2 | 1.1 | Identify requirements and objects | All teams | 2021-10-18 | 2021-10-20
2 | 1.2 | Create backup plan | PM | 2021-10-20 | 2021-10-22
2 | 1.3 | Market research | PM | 2021-10-22 | 2021-10-28 | Prepare surveys
2 | 1.4 | Produce servers | PM | 2021-10-22 | 2021-10-28
2 | 1.5 | Select security provider | PM | 2021-10-24 | 2021-10-29
2 | 1.6 | Implement backup plan | PM | 2010-10-30 | 2021-11-01
1 | 2 | Phase 2: System Design, Build and Testing |  | 2021-11-02 | 2021-11-29
2 | 2.1 | Admin Module Design and Build | Arch & Dev | 2021-11-02 | 2021-11-13
3 | 2.1.1 | Updating and adding products info | Arch & Dev | 2021-11-02 | 2021-11-04
4 | 2.1.1.1 | Adding new products with pictures | Arch & Dev | 2021-11-02 | 2021-11-04
3 | 2.1.2 | Managing sales with order | Arch & Dev | 2021-11-05 | 2021-11-07
3 | 2.1.3 | Updating information of manufacturers. | Arch & Dev | 2021-11-08 | 2021-11-09
3 | 2.1.4 | Free to perform ads at home page | Arch & Dev | 2021-11-10 | 2021-11-13
2 | 2.2 | User Module Design and Build | Arch & Dev | 2021-11-13 | 2021-11-22
3 | 2.2.1 | View list of products | Arch & Dev | 2021-11-14 | 2021-11-16
4 | 2.2.1.1 | Books classification | Arch & Dev | 2021-11-14 | 2020-11-16
3 | 2.2.2 | Tracking books in database | Arch & Dev | 2020-11-17 | 2020-11-19
3 | 2.2.3 | Online ordering | Arch & Dev | 2021-11-20 | 2021-11-22
2 | 2.3 | Testing prototype | QA | 2021-11-23 | 2021-11-25
3 | 2.3.1 | Integration testing, functional testing | QA & SME | 2021-11-23 | 2021-11-25
2 | 2.4 | Go live Testing | QA | 2021-11-26 | 2021-11-28
2 | 2.5 | Document approved build | PM | 2021-11-28 | 2021-11-29
1 | 3 | Phase 3: System Performance |  | 2021-11-30 | 2021-12-14
2 | 3.1 | Install servers | Dev | 2021-11-30 | 2021-12-02
2 | 3.2 | Test connectivity | QA | 2021-12-03 | 2021-12-06
2 | 3.3 | Configure load balancing | QA | 2021-12-06 | 2021-12-09
2 | 3.4 | Performance testing | QA | 2021-12-10 | 2021-12-12
2 | 3.5 | Finish the project | All teams | 2021-12-13 | 2021-12-14